## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
History of Intel Processor | Intro | Task 1.1 | 4 | [10 empty] | 0 | 4
History of Intel Processor | Intro | Task 2.1 | 4
History of Intel Processor | 1971 | Task 3.1 | 4
History of Intel Processor | 1972 | Task 4.1 | 4
History of Intel Processor | 1974 | Task 5.1 | 4
History of Intel Processor | 1978 | Task 6.1 | 4
History of Intel Processor | 1982 | Task 7.1 | 4
History of Intel Processor | 1985 | Task 8.1 | 4
History of Intel Processor | 1989 | Task 9.1 | 4
History of Intel Processor | 1993 | Task 10.1 | 4
History of Intel Processor | 1995 | Task 11.1 | 4
History of Intel Processor | 1997 | Task 12.1 | 4
History of Intel Processor | 1998 | Task 13.1 | 4
History of Intel Processor | 1999 | Task 14.1 | 4
History of Intel Processor | 2000 | Task 15.1 | 4
History of Intel Processor | 2001 | Task 16.1 | 4
History of Intel Processor | 2003 | Task 17.1 | 4
History of Intel Processor | 2006 | Task 18.1 | 4
History of Intel Processor | 2008 | Task 18.2 | 3
History of Intel Processor | 2008 | Task 19.1 | 3
History of Intel Processor | 2010 | Task 20.1 | 4
History of Intel Processor | 2012 | Task 21.1 | 4
History of Intel Processor | 2013 | Task 22.1 | 3
Ideal - Remaining efforts in uninterrupted working hours |  |  | 89 | 81.5833 | 74.1667 | 66.75 | 59.3333 | 51.9167 | 44.5 | 37.0833 | 29.6667 | 22.25 | 14.8333 | 7.4167 | -8.8818e-15
Actual - Remaining efforts in uninterrupted working hours |  |  | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Note on H5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered