## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
History of Intel Processor | Intro | Task 1.1 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | Intro | Task 2.1 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 1971 | Task 3.1 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 1972 | Task 4.1 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 1974 | Task 5.1 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 1978 | Task 6.1 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 1982 | Task 7.1 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 1985 | Task 8.1 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 1989 | Task 9.1 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 1993 | Task 10.1 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 1997 | Task 11.1 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 1998 | Task 12.1 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 1999 | Task 13.1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 2000 | Task 14.1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 2001 | Task 15.1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0
History of Intel Processor | 2003 | Task 16.1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0
History of Intel Processor | 2006 | Task 17.1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0
History of Intel Processor | 2008 | Task 18.1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0
History of Intel Processor | 2008 | Task 19.1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0
History of Intel Processor | 2010 | Task 20.1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0
History of Intel Processor | 2012 | Task 21.1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0
History of Intel Processor | 2013 | Task 22.1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2
Actual - Remaining efforts in uninterrupted working hours |  |  | 85 | 77.9167 | 70.8333 | 63.75 | 56.6667 | 49.5833 | 42.5 | 35.4167 | 28.3333 | 21.25 | 14.1667 | 7.0833 | 0
Ideal - Remaining efforts in uninterrupted working hours |  |  | 85 | 85 | 79 | 72 | 60 | 45 | 40 | 29 | 24 | 20 | 14 | 6 | 2
Note on H5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered